## Week1
| Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
| 6 | 7 | 8 | 9 | 10 | 11 | 12
What happened in project: | Understanding of what is required Type of data invloved Initial planning and test queries to GIATA webservice | Finished Proposal up to standard that I am happy Itial understanding of the process involved throughout the project and what extra learning needs to be done. (c# web services) Will have to relearn angularJS and how to utilise that | Some progress on using angularJS and how to incorperate that into my application Initial Understanding of the data that needs to flow between entities | Tried to figure out how to do some of the problems in project Started initial plan writeup for next meeting with craig | Started doing research as to how I should structure the project. Discussions with current staff about the way they do things and when I can go talk to different people about specific problems
What happened for course: | Created Diary and posted first entry Created a time log in Excel to keep track of hours Worked on Risk analysis for Proposal | Finished Proposal up to standard that I am happy | Wrote in diary + Time schedule Had Buisness analysis that meant I had to go into ara | Finished final proposal and need to send away to respective parties Started reading a book to do with MVCs and c# |  | Read Book | Read Book
Goals Completed: | Turn up on time for work | Finish Risk analysis and sent through my final proposal to Mike Left with lots more questions but made big advancements | Connected to Dev server Beginning to understand the relationships Not mauch initial planning | Proposal checked off | More understanding of SPWA Completed an online tutorial and started looking towards other options | Gained more understanding of how a SPWA works and how to properly structure it
Goals for tomorrow: | Finish Risk Analysis for proposal and have a final version ready for meeting with Mike Meet with technical Tourplan personal and do not leave the meeting with questions | Start detailed planning and initial diagrams Connect through to Dev server Test connections of Tourplan Webservice as well as to GIATA Understand the connection between angularjs and c# | More comprehensive planning with my general idea layed out with work componentry to say it is possible Have my proposal checked off | Need to become more understanding of the single page web application and how to control it. Complete online tutorial | Continue reading and make some notes for methadology report Start a burndown chart of every detail/start detailed planning |  | Do tutorials in book + set up a single page application
Things struggled with: | Getting in contact/finding time to meet with Mike | Connecting through to the Development server on Tourplany system The initial understanding of angularJS | Hard getting my head around angular JS again. Not a complete understanding of what is required but have enough information to get on with some work. Will meet early next week to discuss my progress | Not able to solve some problems that I had with the project Speaking up in the work environment | Concentrating on reading and not getting off task | Staying focused on reading | Staying focused on reading
Notes:

## Week2
| Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
| 6 | 7 | 8 | 9 | 10 | 11 | 12
What happened in project: | Completed a first structured application Started testing out different elements Finished first 3 chapters of the book | Got a more clear understanding of what is required from Tourplan The user interface is being more defined Access questions asked and then allowed in. Can now save to correct repository and set up my own webservices environment | Gained access to my own WebServices environment Started planning / structuring of the project Am now linked into their repository system so can start branching my project | Proposal signed off by industry supervisor. More planning + flow of information | Updated how the Phase1 may need to be structured. Have problem now with sending lots of requests. Meeting with john to confirm right course of action.
What happened for course: | Read book + started a write up for weekly meeting with mike | Continued diary and thought about what to talk about in next section | Did first weekly meeting form for Mike. Continued to do some reading on MVC 5 Was given first assignment for other course | Had meeting with Mike + discussed potential problems + new books. Handed over proposal to Mike then David. | Asked people what they wanted out of QA in this organisation Read Mcconnell chapter on quality assurance Went through Microsoft tutorials and said which ones I could do (content)
Goals Completed: | Head aroundapplication Things started moving together | XML data able to be formatted | Setup webservices environment Tools in my hands now | Testing certain parts complete. Not all working as planned. | Meeting with Joh Monday 3.30 Detailed flow of information
Goals for tomorrow: | Have the XML GIATA data able to be formatted and Manipulated Start a propper planning diary/burndown | Able to set up webservices environment Start planning properly Be set up within own environement | Keep testing the environment. Get key responses back from within my app. Get a logical response from webservices | Create a detailed list of all information and how it will flow around my application Print off all relevant informaion Organise a meeting between John, (Jackson via Lorna) and myself for Monday/Tuesday
Things struggled with: | Googling things over and over as apposed to rembering them. Loss of time. Need to become more familiar with Visual Studio again | Rembering code / efficiency of rembering code Getting started on planning/not letting it just go | Rembering all the processes | Finding the line between following the structure and processes that are prescribed by Tourplan, vs what I know/can provide | Getting over a new problem and finding new solutions to it
Notes:

## Week3
| Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
| 6 | 7 | 8 | 9 | 10 | 11 | 12
What happened in project: | Got over hurdle of being many web requests. Moving on with Giata connections | Running into trouble with response times from Giata. Over 1 min to get one request for 1000 giata IDs
What happened for course: | Read up on book. Started looking for more books
Goals Completed: |  | Can connect through to Giata with multiple IDs…. Caused another problem
Goals for tomorrow: | Create propper burn down chart + start propper planning after Johns advice | Have an understanding/Clear path of where to go. Is this project even viable
Things struggled with: | Confidence in going into Johns office knowing what I am talking about and understanding what he is going on about | Getting over hurdles + waiting for responces from people as to direction of project. Ever changing program/requirements changing
Notes:

## Template
| Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
| 6 | 7 | 8 | 9 | 10 | 11 | 12
What happened in project:
What happened for course:
Goals Completed:
Goals for tomorrow:
Things struggled with:
Notes: